## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Setup of project environment (JDK, Spring, DB) | MUST HAVE |  | Self | 3- Completed
S1 | S1 | US-02 | Implement Task CRUD using Thymeleaf UI | MUST HAVE | US-01 | Self | 3- Completed
S1 | S1 | US-03 | Add filters, sorting & pagination in UI | MUST HAVE | US-02 | Self | 3- Completed
S1 | S1 | US-04 | Add enums (Status, Priority) + Ul improvements | MUST HAVE | US-02 | Self | 3- Completed
S2 | S2 | US-01 | Implement REST APIs for Task CRUD | SHOULD HAVE | US-02 (S1) | Self | 3- Completed
S2 | S2 | US-02 | Add REST filtering, sorting & pagination | MUST HAVE | US-01 | Self | 3- Completed
S2 | S2 | US-03 | API testing via Postman + final cleanup | MUST HAVE | US-02 | Self | 3- Completed
S3 | S3 | US-01 | User registration using email and password, including storing user details in the database. | MUST HAVE | US-03 (S2) | Self | 3- Completed
S3 | S3 | US-02 | Generate and send OTP to the user's email and verify the OTP to activate the account. | MUST HAVE | US-01 | Self | 3- Completed
S3 | S3 | US-03 | User login functionality using email and password, validating credentials against the database. | MUST HAVE | US-01 | Self | 3- Completed
S3 | S3 | US-04 | Maintain authenticated user session to ensure only logged-in users can access their own tasks. | MUST HAVE | US-03 | Self | 3- Completed
S4 | S4 | US-01 | Implement task completion tracking & insights | SHOULD HAVE | US-04 (S3) | Self | 3- Completed
S4 | S4 | US-02 | Build dashboard with visual analytics | SHOULD HAVE | US-01 | Self | 3- Completed
S4 | S4 | US-03 | Add user profile & secure password management | MUST HAVE | US-04 (S3) | Self | 3- Completed
S4 | S4 | US-04 | Multi-language support & full deployment | SHOULD HAVE | US-02 | Self | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T1 | Install JDK & configure environment variables | 2025-11-27 | 2025-11-27 | Anurag Singh | Setup | Completed | 2
US-01 | T2 | Create Spring Boot project & setup dependencies | 2025-11-28 | 2025-11-28 | Anurag Singh | Setup | Completed | 3
US-01 | T3 | Configure database (MySQL) & connection | 2025-11-29 | 2025-11-30 | Anurag Singh | Setup | Completed | 3
US-02 | T4 | Design Task entity & repository | 2025-12-01 | 2025-12-02 | Anurag Singh | Coding | Completed | 2
US-02 | T5 | Implement Create & Read task functionality | 2025-12-03 | 2025-12-04 | Anurag Singh | Coding | Completed | 4
US-02 | T6 | Implement Update & Delete task functionality | 2025-12-05 | 2025-12-06 | Anurag Singh | UI | Completed | 3
US-03 | T7 | Implement pagination logic in backend | 2025-12-11 | 2025-12-12 | Anurag Singh | Coding | Completed | 3
US-03 | T8 | OTP &Email Integration | 2025-12-13 | 2025-12-14 | Anurag Singh | Automation | Completed | 4
US-03 | T9 | Add sorting & filter options in UI | 2025-12-15 | 2025-12-16 | Anurag Singh | UI | Completed | 3
US-03 | T10 | Test UI behavior with large data | 2025-12-17 | 2025-12-18 | Anurag Singh | Testing | Completed | 2
US-04 | T10 | Create Status & Priority enums | 2025-12-19 | 2025-12-20 | Anurag Singh | Coding | Completed | 4
US-04 | T11 | CSV Export &Mail Report | 2025-12-22 | 2025-12-24 | Anurag Singh | Coding | Completed | 3
US-04 | T12 | Integrate enums with task entity & UI | 2025-12-27 | 2025-12-28 | Anurag Singh | UI | Completed | 3
US-04 | T13 | UI enhancements & final testing | 2026-01-03 | 2026-01-05 | Anurag Singh | Development | Completed | 4
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7